## PRs_Gantt
Número PR | Título PR | Rama Origen | Rama Destino | Autor | Aprobado Por | Fecha Creación | Fecha Aprobación | Fecha Merge | Fecha Inicio (Gantt) | Fecha Fin (Gantt) | Duración (Días)
1 | Dev | dev | main | vvu981 | Merge Directo / Admin | 2026-06-01 10:16 | 2026-06-01 10:16 | 2026-06-01 10:16 | 2026-06-01 | 2026-06-01 | 1
2 | Refactor web layer and enforce DTO validation for user UUID | feat/user | dev | vvu981 | Merge Directo / Admin | 2026-06-28 12:33 | 2026-06-28 12:34 | 2026-06-28 12:34 | 2026-06-28 | 2026-06-28 | 1
3 | Add email service and tests for user feature | feat/user | dev | vvu981 | Merge Directo / Admin | 2026-06-29 12:08 | 2026-06-29 12:11 | 2026-06-29 12:11 | 2026-06-29 | 2026-06-29 | 1
28 | Update GitHub CLI commands and fix Docker Compose issues | feat/user | dev | vvu981 | Merge Directo / Admin | 2026-06-29 15:28 | 2026-06-29 15:30 | 2026-06-29 15:30 | 2026-06-29 | 2026-06-29 | 1
29 | Enhance accommodations service with features, tests, and coverage | feat/accommodations | dev | vvu981 | Merge Directo / Admin | 2026-07-05 17:43 | 2026-07-05 17:44 | 2026-07-05 17:44 | 2026-07-05 | 2026-07-05 | 1
30 | Fix/auth jwt banned 403 | fix/auth-jwt-banned-403 | dev | vvu981 | Merge Directo / Admin | 2026-07-06 17:47 | 2026-07-06 17:48 | 2026-07-06 17:48 | 2026-07-06 | 2026-07-06 | 1
31 | feat(security): transversal user status enforcement layer | fix/user-permissions | dev | vvu981 | Merge Directo / Admin | 2026-07-10 11:36 | 2026-07-10 11:48 | 2026-07-10 11:48 | 2026-07-10 | 2026-07-10 | 1
32 | Feat/booking requests v2 | feat/bookingRequests-v2 | dev | vvu981 | Merge Directo / Admin | 2026-07-13 14:19 | 2026-07-13 14:27 | 2026-07-13 14:27 | 2026-07-13 | 2026-07-13 | 1
33 | Refactor accommodation module for stateless security with UserPrincipal and UUIDs | refactor/use-uuid-in-controllers | dev | vvu981 | Merge Directo / Admin | 2026-07-13 21:48 | 2026-07-13 21:50 | 2026-07-13 21:50 | 2026-07-13 | 2026-07-13 | 1
34 | Add E2E integration test for BookingRequests | feat/booking-requests-e2e-tests | dev | vvu981 | Merge Directo / Admin | 2026-07-13 22:15 | 2026-07-13 22:16 | 2026-07-13 22:16 | 2026-07-13 | 2026-07-13 | 1
35 | refactor(core): decouple domain exceptions from web layer | feat/solid-exceptions-refactor | dev | vvu981 | Merge Directo / Admin | 2026-07-15 12:38 | 2026-07-15 12:41 | 2026-07-15 12:41 | 2026-07-15 | 2026-07-15 | 1
36 | feat(booking): implement strict month validation and concurrency fixes | feature/booking-month-validation | dev | vvu981 | Merge Directo / Admin | 2026-07-15 13:31 | 2026-07-15 13:33 | 2026-07-15 13:33 | 2026-07-15 | 2026-07-15 | 1
37 | refactor: optimize core domains for SOLID, concurrency, and transactional consistency | refactor/solid-events-lock | dev | vvu981 | Merge Directo / Admin | 2026-07-15 17:34 | 2026-07-15 17:35 | 2026-07-15 17:35 | 2026-07-15 | 2026-07-15 | 1
38 | feat(home): Implementación completa del módulo de Hogares | feat/home | dev | vvu981 | Merge Directo / Admin | 2026-07-31 10:36 | 2026-08-07 09:15 | 2026-08-07 09:15 | 2026-07-31 | 2026-08-07 | 7
39 | Feat/expenses module | feat/expenses-module | dev | vvu981 | Merge Directo / Admin | 2026-08-07 14:08 | 2026-08-08 11:11 | 2026-08-08 11:11 | 2026-08-07 | 2026-08-08 | 1
40 | feat(home): implement Activity Log module and formatting strategy | feat/activity-log-module | dev | vvu981 | Merge Directo / Admin | 2026-08-09 10:18 | 2026-08-09 11:15 | 2026-08-09 11:15 | 2026-08-09 | 2026-08-09 | 1
41 | Refactor/core architecture | refactor/core-architecture | dev | vvu981 | Merge Directo / Admin | 2026-08-09 11:35 | 2026-08-09 18:45 | 2026-08-09 18:45 | 2026-08-09 | 2026-08-09 | 1
42 | Implement reports and moderation module | feat/reports-module | dev | vvu981 | Merge Directo / Admin | 2026-08-09 19:29 | 2026-08-09 22:15 | 2026-08-09 22:15 | 2026-08-09 | 2026-08-09 | 1
43 | Implement admin accommodation search and password recovery features | feat/password-recovery-and-profiles | dev | vvu981 | Merge Directo / Admin | 2026-08-10 11:27 | 2026-08-10 11:53 | 2026-08-10 11:53 | 2026-08-10 | 2026-08-10 | 1
44 | Add security deposit feature and improve test coverage | feat/backend-fianza-payments | dev | vvu981 | Merge Directo / Admin | 2026-08-11 22:21 | 2026-08-13 10:22 | 2026-08-13 10:22 | 2026-08-11 | 2026-08-13 | 2
45 | Implement recent search history and recommendation system | feature/recommendation-system | dev | vvu981 | Merge Directo / Admin | 2026-08-13 16:55 | 2026-08-13 18:29 | 2026-08-13 18:29 | 2026-08-13 | 2026-08-13 | 1
46 | feat(auth): implement Google Sign-in flow | feat/frontend-layout | dev | vvu981 | Merge Directo / Admin | 2026-08-14 08:41 | 2026-08-14 09:15 | 2026-08-14 09:15 | 2026-08-14 | 2026-08-14 | 1
47 | Implement profile editing feature | feat/frontend-miPerfil | dev | vvu981 | Merge Directo / Admin | 2026-08-14 10:33 | 2026-08-14 10:51 | 2026-08-14 10:51 | 2026-08-14 | 2026-08-14 | 1
48 | Implement password reset flow and update configuration | feat/frontend-forgetPassword | dev | vvu981 | Merge Directo / Admin | 2026-08-14 11:37 | 2026-08-14 16:58 | 2026-08-14 16:58 | 2026-08-14 | 2026-08-14 | 1
49 | Manage Accommodation & AccommodationListing (Frontend) | feat/accommodation-&-listing | dev | vvu981 | Merge Directo / Admin | 2026-08-23 15:16 | 2026-08-24 13:17 | 2026-08-24 13:17 | 2026-08-23 | 2026-08-24 | 1
50 | Enhance housing features with filters, map optimizations, and details | feat/frontend-accommodationListing | dev | vvu981 | Merge Directo / Admin | 2026-08-26 19:37 | 2026-08-27 22:50 | 2026-08-27 22:50 | 2026-08-26 | 2026-08-27 | 1
51 | feat(booking-requests): implement booking request management, detail modal, deep-linking, and email notifications | feat/bookingRequests | dev | vvu981 | Merge Directo / Admin | 2026-08-29 16:45 | 2026-08-30 14:54 | 2026-08-30 14:54 | 2026-08-29 | 2026-08-30 | 1
52 | Add 404 page and protect profile route | feat/pageNotFound | dev | vvu981 | Merge Directo / Admin | 2026-08-30 15:01 | 2026-08-30 15:01 | 2026-08-30 15:01 | 2026-08-30 | 2026-08-30 | 1
53 | Add complete listing reporting functionality with validations and UI | feat/denuncia | dev | vvu981 | Merge Directo / Admin | 2026-08-30 15:23 | 2026-08-30 15:30 | 2026-08-30 15:30 | 2026-08-30 | 2026-08-30 | 1
54 | Implement public user profile page with security and navigation features | feat/profileUsers | dev | vvu981 | Merge Directo / Admin | 2026-08-30 16:45 | 2026-08-30 16:55 | 2026-08-30 16:55 | 2026-08-30 | 2026-08-30 | 1
55 | feat(housing): expand amenity catalog with popular coliving amenities | feat/addAmenities | dev | vvu981 | Merge Directo / Admin | 2026-08-30 17:11 | 2026-08-30 17:13 | 2026-08-30 17:13 | 2026-08-30 | 2026-08-30 | 1
56 | Implement verified reviews and complete report feedback system | feat/reports | dev | vvu981 | Merge Directo / Admin | 2026-09-01 10:56 | 2026-09-01 10:56 | 2026-09-01 10:56 | 2026-09-01 | 2026-09-01 | 1
57 | Implement active moderation ranking and cascade resolution features | feat/admin | dev | vvu981 | Merge Directo / Admin | 2026-09-02 10:53 | 2026-09-02 11:32 | 2026-09-02 11:32 | 2026-09-02 | 2026-09-02 | 1
58 | Implement household management module and integrate with layout | feat/home | dev | vvu981 | Merge Directo / Admin | 2026-09-02 13:43 | 2026-09-03 10:29 | 2026-09-03 10:29 | 2026-09-02 | 2026-09-03 | 1
59 | Enhance expense management with editing, debt payments, and audits | feat/expenses | dev | vvu981 | Merge Directo / Admin | 2026-09-03 14:14 | 2026-09-03 22:44 | 2026-09-03 22:44 | 2026-09-03 | 2026-09-03 | 1
60 | feat(user): implement soft delete and account reactivation in frontend | feat/delete-account | dev | vvu981 | Merge Directo / Admin | 2026-09-04 11:10 | 2026-09-04 11:19 | 2026-09-04 11:19 | 2026-09-04 | 2026-09-04 | 1
61 | Implement chores management, leaderboard, and recurring tasks | feat/tasks | dev | vvu981 | Merge Directo / Admin | 2026-09-06 11:14 | 2026-09-06 14:18 | 2026-09-06 14:18 | 2026-09-06 | 2026-09-06 | 1
62 | Implement in-app messaging and reporting with tests | feat/messages | dev | vvu981 | Merge Directo / Admin | 2026-09-07 18:28 | 2026-09-08 22:12 | 2026-09-08 22:12 | 2026-09-07 | 2026-09-08 | 1
63 | Integrate MCP server, Spring AI orchestrator, and React Copilot widget | feat/mcp | dev | vvu981 | Merge Directo / Admin | 2026-09-10 11:03 | 2026-09-12 22:00 | 2026-09-12 22:00 | 2026-09-10 | 2026-09-12 | 2
64 | Improve responsive layout and mobile navigation ergonomics | feat/responsive | dev | vvu981 | Merge Directo / Admin | 2026-09-17 09:19 | 2026-09-17 09:23 | 2026-09-17 09:23 | 2026-09-17 | 2026-09-17 | 1
65 | Feat: Android APK | feat/capacitor-android | dev | vvu981 | Merge Directo / Admin | 2026-09-21 09:01 | 2026-09-21 09:46 | 2026-09-21 09:46 | 2026-09-21 | 2026-09-21 | 1
66 | feat(compliance): add GDPR/LOPDGDD compliance layer with CMP, legal p… | feat/terms | dev | vvu981 | Merge Directo / Admin | 2026-09-21 13:45 | 2026-09-21 13:47 | 2026-09-21 13:47 | 2026-09-21 | 2026-09-21 | 1